## Defects_v1
Bug Report Template
Project Name |  |  | Banking System |  |  | Manual Testing
Raised By |  |  | Seif Aldin Yasser
Assigned to |  |  | Development Team
Software Version |  |  | V1
Date |  |  | 13/10/2024
Defect_ID | Test Case_ID | Summary | Steps to Reproduce | Expected result | Actual Result | Enviroment | Eviedence | Priority | Severity | Status
1 | NC_4 | When I enter a First character blank space in Name Field it showed Number are not allowed | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown In Name Field | An error message "Numbers are not allowed" is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
2 | NC_5 | When I don’t enter a value in address field it is not showed any error messages | 1) Do not enter a value in ADDRESS Field 2) Press TAB and move to next Field | An error message "ADDRESS cannot be empty" must be shown in Address Field | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
3 | NC_6 | When I enter a First character blank space in Address Field it is not showed any error messages | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in Address Field | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
4 | NC_7 | When I enter a First character blank space in City Field it showed Number are not allowed | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in City Field | An error message "Numbers are not allowed" is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
5 | NC_11 | When I enter a First character blank space in State Field it showed Number are not allowed | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in State Field | An error message "Numbers are not allowed" is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
6 | NC_20 | When I enter a First character blank space in Pin Field it showed Number are not allowed | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in Pin Field | An error message Numbers are not allowed" is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
7 | NC_23 | When I enter a First character blank space in Telephone Field it showed Number are not allowed | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in Telephone Field | An error message "Characters are not allowed" is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
8 | EC_4 | When I enter a valid Cutomer id and press submit it showed connection error | 1) Enter valid Customer id 2) Submit | Edit Customer successfully redirect to Edit Customer Page | "Connection Error is shown "" Warning: mysql_connect() [function.mysql-connect]: Access denied for user 'root'@'localhost' (using password: NO) in /home/demo/public_html/V1/html/editCustomerPage.php on line 3 could not connect Access denied for user 'root'@'localhost' (using password: NO) """ | Chrome, Firefox, and Edge |  | High | High | Open
9 | EC_5 | When I don’t enter a value in Name Field then press tab to move to next field it showed connection error | 1) Do not enter a value in NAME Field 2) Press TAB and move to next Field | An error message "Name cannot be empty" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
10 | EC_6 | When I enter a numeric value in Name Field then press tab to move to next field it showed connection error | 1) Enter numeric value in NAME Field | An error message "Name cannot contain numbers" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
11 | EC_7 | When I enter a special character value in Name Field then press tab to move to next field it showed connection error | 1) Enter Special Character In NAME Field | An error message "Name cannot contain Special Characters" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
12 | EC_8 | When I don’t enter a value in Address Field then press tab to move to next field it showed connection error | 1) Do not enter a value in ADDRESS Field 2) Press TAB and move to next Field | An error message "ADDRESS cannot be empty" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
13 | EC_9 | When I don’t enter a value in City Field then press tab to move to next field it showed connection error | 1) Do not enter a value in CITY Field 2) Press TAB and move to next Field | An error message "CITY cannot be empty" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
14 | EC_10 | When I enter a numeric value in City Field then press tab to move to next field it showed connection error | 1) Enter numeric value in CITY Field | An error message "City cannot contain Number" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
15 | EC_11 | When I enter a special character value in City Field then press tab to move to next field it showed connection error | 1) Enter Special Character In CITY Field | An error message "City cannot contain Special Characters" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
16 | EC_12 | When I don’t enter a value in State Field then press tab to move to next field it showed connection error | 1) Do not enter a value in STATE Field 2) Press TAB and move to next Field | An error message "STATE cannot be empty" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
17 | EC_13 | When I enter a numeric value in State Field then press tab to move to next field it showed connection error | 1) Enter numeric value in STATE Field | An error message "Numbers are not allowed" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
18 | EC_14 | When I enter a special character value in State Field then press tab to move to next field it showed connection error | 1) Enter Special Character In STATE Field | An error message "City cannot contain Special Characters" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
19 | EC_15 | When I enter a character value in Pin Field then press tab to move to next field it showed connection error | 1) Enter character value in PIN Field | An error message "PIN cannot contain character" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
20 | EC_16 | When I don’t enter a value in Pin Field then press tab to move to next field it showed connection error | 1) Do not enter a value in PIN Field 2) Press TAB and move to next Field | An error message "PIN cannot be empty" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
21 | EC_17 | When I enter a less or more than 6 digit value in Pin Field it showed connection error | 1) Enter More than 6 digit in PIN field 2) Enter Less Than 6 digit in PIN field | An error message "PIN must contain 6 digit" | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
22 | EC_18 | When I enter a special character value in Pin Field then press tab to move to next field it showed connection error | 1) Enter Special Character In PIN Field | An error message "PIN cannot contain Special Characters" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
23 | EC_19 | When I don’t enter a value in Telephone Field then press tab to move to next field it showed connection error | 1) Do not enter a value in Telephone Field 2) Press TAB and move to next Field | An error message "Telephone cannot be empty" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
24 | EC_20 | When I enter a special character value in Pin Field then press tab to move to next field it showed connection error | 1) Enter Special Character In PIN Field | An error message "Telephone cannot contain Special Characters" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
25 | EC_21 | When I don’t enter a value in Email Field then press tab to move to next field it showed connection error | 1) Do not enter a value in Email Field 2) Press TAB and move to next Field | An error message "Email cannot be empty" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
26 | EC_22 | When I enter a invalid value in Email Field then press tab to move to next field it showed connection error | 1) Enter invalid email in Email field | An error message "Email must be in format example@example.com" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
27 | NA_2 | When I enter a character value in Customer ID Field it showed no error | 1) Enter character value in Customer id Field | An error message "Customer id must be numeric" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
28 | NA_3 | When I enter a special character value in Customer ID Field it showed no error | 1) Enter Special Character In Customer id Field | An error message "Customer id cannot have special character" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
29 | NA_4 | When I enter a blank space in Customer ID Field it showed no error | 1) Customer Id cannot have Blank space 2) Press Tab | An error message "Customer id cannot have blank space" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
30 | NA_5 | When I enter a first characther space in Customer ID Field it showed no error | 1) Enter first character space 2) Press Tab | An error message "Customer id cannot have first character space" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
31 | NA_6 | When I don’t enter value in Deposit Field it showed no error | 1) Do not enter a value in Initial Deposit Field 2) Press TAB and move to next Field | An error message "Initial deposit cannot be empty" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
32 | NA_7 | When I enter character value in Deposit Field it showed no error | 1) Enter character value in Initial Deposit Field | An error message "Initial Deposit must be numeric" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
33 | NA_8 | When I enter special character value in Intial Deposit Field it showed no error | 1) Enter Special Character In Initial Deposit Field | An error message "Initial Deposit cannot have special character" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
34 | NA_9 | When I enter blank space in Initial Deposit Field it showed no error | 1) Initial Deposit cannot have Blank space 2) Press Tab | An error message "Initial Deposit cannot have blank space" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
35 | NA_10 | When I enter a first characther space in Initial Deposit Field it showed no error | 1) Enter first character space 2) Press Tab | An error message "Initial Deposit cannot have first character space" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
36 | EA_4 | When I enter a valid account number in Edit Account Field it showed no connection error | 1) Enter valid Account Number 2) Submit | Edit Account successfully redirect to Edit Account Form | Connection Error is shown " Warning: mysql_connect() [function.mysql-connect]: Access denied for user 'root'@'localhost' (using password: NO) in /home/demo/public_html/V1/html/editCustomerPage.php on line 3 could not connect Access denied for user 'root'@'localhost' (using password: NO) " | Chrome, Firefox, and Edge |  | High | High | Open
37 | EA_7 | When I don’t enter value in Customer ID Field it showed no connection error | 1) Do not enter a value in Customer id Field 2) Press TAB and move to next Field | An error message "Customer id cannot be empty" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
38 | EA_8 | When I enter value in Customer ID Field it showed no connection error | 1) Enter character value in Customer id Field | An error message "Customer id must be numeric" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
39 | EA_9 | When I enter special character value in Customer ID Field it showed no connection error | 1) Enter Special Character In Customer id Field | An error message "Customer id cannot have special character" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
40 | EA_10 | When I enter a blank space in Customer ID Field it showed no connection error | 1) Customer Id cannot have Blank space 2) Press Tab | An error message "Customer id cannot have blank space" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
41 | EA_11 | When I enter a first character space in Customer ID Field it showed no connection error | 1) Enter first character space 2) Press Tab | An error message "Customer id cannot have first character space" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
42 | EA_12 | When I don’t enter value in Balance Field it showed no connection error | 1) Do not enter a value in Balance Field 2) Press TAB and move to next Field | An error message "Balance cannot be empty" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
43 | EA_13 | When I enter a character value in Balance Field it showed no connection error | 1) Enter character value in Balance Field | An error message "Balance must be numeric" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
44 | EA_14 | When I enter a special character value in Balance Field it showed no connection error | 1) Enter Special Character In Balance Field | An error message "Balance cannot have special character" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
45 | EA_15 | When I enter a blank space in Balance Field it showed no connection error | 1) Balance cannot have Blank space 2) Press Tab | An error message "Balance cannot have blank space" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
46 | EA_16 | When I enter a first character space in Balance Field it showed no connection error | 1) Enter first character space 2) Press Tab | An error message "Balance cannot have first character space" must be shown | Cannot be executed due to connection issue | Chrome, Firefox, and Edge |  | High | High | Open
47 | DC_4 | When I enter a blank space in Customer ID Field it showed no connection error | 1) Customer ID cannot have Blank space 2) Press Tab | An error message "Customer ID cannot have blank space" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
48 | DC_5 | When I enter a first character space in Customer ID Field it showed no connection error | 1) Enter first character space 2) Press Tab | An error message "Customer ID cannot have first character space" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
49 | CS_4 | When I enter a blank space in Account Number Field it showed Character are not allowed | 1) Account no cannot have Blank space 2) Press Tab | An error message "Account no cannot have blank space" must be shown | An error message "Characters are not allowed" must be shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
50 | CS_6 | When I don’t enter value in Amount Field it showed no connection error | 1) Do not enter a value in Amount Field 2) Press TAB and move to next Field | An error message "Amount Lower Limit cannot be empty" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
51 | CS_7 | When I enter lower limit number value in Amount Field it showed no error | 1) Enter numeric value in Amount Lower Limit number Field | An error message "Amount Lower Limit must be numeric" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
52 | CS_8 | When I enter special character value in Amount Field it showed no error | 1) Enter Special Character In Amount Field | An error message "Amount Lower Limit cannot have special character" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
53 | CS_9 | When I enter a blank space in Amount Number Number Field it showed no error | 1) Amount no cannot have Blank space 2) Press Tab | An error message "Amount Lower Limit cannot have blank space" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
54 | CS_10 | When I enter a first character space in Amount Field it showed no error | 1) Enter first character space 2) Press Tab | An error message "Amount Lower Limit cannot have first character space" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
55 | CS_11 | When I don’t enter value in Amount Field then press tab it showed no error | 1) Do not enter a value in Number of Transaction Field 2) Press TAB and move to next Field | An error message "Number of Transaction cannot be empty" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
56 | CS_12 | When I enter a character value in Number of trasnaction Field it showed no error | 1) Enter character value in Number of Transaction number Field | An error message "Number of Transaction must be numeric" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
57 | CS_13 | When I enter special character value in Number of transaction Field it showed no error | 1) Enter Special Character In Number for Transaction Field | An error message "Number of Transaction cannot have special character" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
58 | CS_14 | When I enter a blank space in Number of transaction Field it showed no error | 1) Number of transaction cannot have Blank space 2) Press Tab | An error message "Number of Transaction cannot have blank space" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
59 | CS_15 | When I enter a first character space in Number of transaction Field then press tab it showed no error | 1) Enter first character space 2) Press Tab | An error message "Number Of Transaction cannot have first character space" must be shown | No error message is shown | Chrome, Firefox, and Edge |  | Medium | Medium | Open
60 | IP_1 | When I enter a value of all required fields i then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display "Customer added successfully !!" | Warning: mysql_connect() [function.mysql-connect]: Access denied for user 'root'@'localhost' (using password: NO) in /home/demo/public_html/V1/html/insrtCustomer.php on line 2 Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Chrome, Firefox, and Edge |  | High | High | Open
61 | IP_2 | When I enter a value of all required fields with existed user i then press submit it showed connection error | 1) Enter all required field with existing user data 2) Submit | Message Should be displayed"Email address already exist" | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
62 | IP_3 | When I enter a value of all required fields uo update records then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be displayed" customer records updated successfully!!" | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
63 | IP_4 | When I enter a value of all required fields uo update records then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display" customer records updated successfully!!" | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
64 | IP_5 | When I enter a value of all required fields to update records then press submit it showed connection error | 1) Enter the required fields 2) Submit | Message Should be display" You are not authorise to edit this customer!!" | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
65 | IP_6 | When I enter a value of all required fields to generate account then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display " account generated successfully" | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
66 | IP_7 | When I enter a value of all required fields with customer id and then press submit it showed connection error | 1) Enter all fields with customer id and account type already exist | Message Should be display " account generated successfully" | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
67 | IP_8 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter Account Number 2) Submit | Display Generated ministatement | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
68 | IP_9 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter account number 2) Submit | Message Should be display " account detail successfully updated" | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
69 | IP_10 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter all required fields 2) Submit | Display Generated ministatement | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
70 | IP_11 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display"Account deleted Successfully" | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
71 | IP_12 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display"Account does not exist " | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
72 | IP_13 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display"Account does not exist " | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
73 | IP_14 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1)Enter all required field of deleted account 2)Submit | Message Should be display - "Account does not exist" | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
74 | IP_15 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display"Customer could not be deleted " | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
75 | IP_16 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1)Enter all required field of deleted account 2)Submit | Message Should be display"You are not authorise to delete this account " | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
76 | IP_17 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter Account Number 2) Submit | Displayed Generated ministatement | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
77 | IP_18 | when I enter value of all required field then press submit it showed connection error | 1) Enter all required fields 2) Submit | Display Generated Customized statement | Connection Error | Chrome, Firefox, and Edge |  | High | High | Open
78 | Exploratory Testing | When I check the name of website it showed Gtpl Bank. | Check the Name of the Website | Guru99 Bank | Gtpl Bank | Chrome, Firefox, and Edge |  | High | Low | Open

## Defects_v2
Bug Report Template
Project Name |  |  | Banking System |  |  | Manual Testing
Raised By |  |  | Seif Aldin Yasser
Assigned to |  |  | Development Team
Software Version |  |  | V2
Date |  |  | 14/10/2024
Defect_ID | Test Case_ID | Summary | Steps to Reproduce | Expected result | Actual Result | Enviroment | Priority | Severity | Status
1 | NC_4 | When I enter a First character blank space in Name Field it showed Number are not allowed | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown In Name Field | An error message "First character cannot be space" must be shown In Name Field | Chrome, Firefox, and Edge | Medium | Medium | Closed
2 | NC_5 | When I don’t enter a value in address field it is not showed any error messages | 1) Do not enter a value in ADDRESS Field 2) Press TAB and move to next Field | An error message "ADDRESS cannot be empty" must be shown in Address Field | An error message "ADDRESS cannot be empty" must be shown in Address Field | Chrome, Firefox, and Edge | Medium | Medium | Closed
3 | NC_6 | When I enter a First character blank space in Address Field it is not showed any error messages | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in Address Field | An error message "First character cannot be space" must be shown in Address Field | Chrome, Firefox, and Edge | Medium | Medium | Closed
4 | NC_7 | When I enter a First character blank space in City Field it showed Number are not allowed | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in City Field | An error message "First character cannot be space" must be shown in City Field | Chrome, Firefox, and Edge | Medium | Medium | Closed
5 | NC_11 | When I enter a First character blank space in State Field it showed Number are not allowed | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in State Field | An error message "First character cannot be space" must be shown in State Field | Chrome, Firefox, and Edge | Medium | Medium | Closed
6 | NC_20 | When I enter a First character blank space in Pin Field it showed Number are not allowed | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in Pin Field | An error message "First character cannot be space" must be shown in Pin Field | Chrome, Firefox, and Edge | Medium | Medium | Closed
7 | NC_23 | When I enter a First character blank space in Telephone Field it showed Number are not allowed | 1) Enter First character Blank space | An error message "First character cannot be space" must be shown in Telephone Field | An error message "First character cannot be space" must be shown in Telephone Field | Chrome, Firefox, and Edge | Medium | Medium | Closed
8 | EC_4 | When I enter a valid Cutomer id and press submit it showed connection error | 1) Enter valid Customer id 2) Submit | Edit Customer successfully redirect to Edit Customer Page | Edit Customer successfully redirect to Edit Customer Page | Chrome, Firefox, and Edge | High | High | Closed
9 | EC_5 | When I don’t enter a value in Name Field then press tab to move to next field it showed connection error | 1) Do not enter a value in NAME Field 2) Press TAB and move to next Field | An error message "Name cannot be empty" must be shown | An error message "Name cannot be empty" must be shown | Chrome, Firefox, and Edge | High | High | Closed
10 | EC_6 | When I enter a numeric value in Name Field then press tab to move to next field it showed connection error | 1) Enter numeric value in NAME Field | An error message "Name cannot contain numbers" must be shown | An error message "Name cannot contain numbers" must be shown | Chrome, Firefox, and Edge | High | High | Closed
11 | EC_7 | When I enter a special character value in Name Field then press tab to move to next field it showed connection error | 1) Enter Special Character In NAME Field | An error message "Name cannot contain Special Characters" must be shown | An error message "Name cannot contain Special Characters" must be shown | Chrome, Firefox, and Edge | High | High | Closed
12 | EC_8 | When I don’t enter a value in Address Field then press tab to move to next field it showed connection error | 1) Do not enter a value in ADDRESS Field 2) Press TAB and move to next Field | An error message "ADDRESS cannot be empty" must be shown | An error message "ADDRESS cannot be empty" must be shown | Chrome, Firefox, and Edge | High | High | Closed
13 | EC_9 | When I don’t enter a value in City Field then press tab to move to next field it showed connection error | 1) Do not enter a value in CITY Field 2) Press TAB and move to next Field | An error message "CITY cannot be empty" must be shown | An error message "CITY cannot be empty" must be shown | Chrome, Firefox, and Edge | High | High | Closed
14 | EC_10 | When I enter a numeric value in City Field then press tab to move to next field it showed connection error | 1) Enter numeric value in CITY Field | An error message "City cannot contain Number" must be shown | An error message "City cannot contain Number" must be shown | Chrome, Firefox, and Edge | High | High | Closed
15 | EC_11 | When I enter a special character value in City Field then press tab to move to next field it showed connection error | 1) Enter Special Character In CITY Field | An error message "City cannot contain Special Characters" must be shown | An error message "City cannot contain Special Characters" must be shown | Chrome, Firefox, and Edge | High | High | Closed
16 | EC_12 | When I don’t enter a value in State Field then press tab to move to next field it showed connection error | 1) Do not enter a value in STATE Field 2) Press TAB and move to next Field | An error message "STATE cannot be empty" must be shown | An error message "STATE cannot be empty" must be shown | Chrome, Firefox, and Edge | High | High | Closed
17 | EC_13 | When I enter a numeric value in State Field then press tab to move to next field it showed connection error | 1) Enter numeric value in STATE Field | An error message "Numbers are not allowed" must be shown | An error message "Numbers are not allowed" must be shown | Chrome, Firefox, and Edge | High | High | Closed
18 | EC_14 | When I enter a special character value in State Field then press tab to move to next field it showed connection error | 1) Enter Special Character In STATE Field | An error message "City cannot contain Special Characters" must be shown | An error message "City cannot contain Special Characters" must be shown | Chrome, Firefox, and Edge | High | High | Closed
19 | EC_15 | When I enter a character value in Pin Field then press tab to move to next field it showed connection error | 1) Enter character value in PIN Field | An error message "PIN cannot contain character" must be shown | An error message "PIN cannot contain character" must be shown | Chrome, Firefox, and Edge | High | High | Closed
20 | EC_16 | When I don’t enter a value in Pin Field then press tab to move to next field it showed connection error | 1) Do not enter a value in PIN Field 2) Press TAB and move to next Field | An error message "PIN cannot be empty" must be shown | An error message "PIN cannot be empty" must be shown | Chrome, Firefox, and Edge | High | High | Closed
21 | EC_17 | When I enter a less or more than 6 digit value in Pin Field it showed connection error | 1) Enter More than 6 digit in PIN field 2) Enter Less Than 6 digit in PIN field | An error message "PIN must contain 6 digit" | An error message "PIN must contain 6 digit" | Chrome, Firefox, and Edge | High | High | Closed
22 | EC_18 | When I enter a special character value in Pin Field then press tab to move to next field it showed connection error | 1) Enter Special Character In PIN Field | An error message "PIN cannot contain Special Characters" must be shown | An error message "PIN cannot contain Special Characters" must be shown | Chrome, Firefox, and Edge | High | High | Closed
23 | EC_19 | When I don’t enter a value in Telephone Field then press tab to move to next field it showed connection error | 1) Do not enter a value in Telephone Field 2) Press TAB and move to next Field | An error message "Telephone cannot be empty" must be shown | An error message "Telephone cannot be empty" must be shown | Chrome, Firefox, and Edge | High | High | Closed
24 | EC_20 | When I enter a special character value in Pin Field then press tab to move to next field it showed connection error | 1) Enter Special Character In PIN Field | An error message "Telephone cannot contain Special Characters" must be shown | An error message "Telephone cannot contain Special Characters" must be shown | Chrome, Firefox, and Edge | High | High | Closed
25 | EC_21 | When I don’t enter a value in Email Field then press tab to move to next field it showed connection error | 1) Do not enter a value in Email Field 2) Press TAB and move to next Field | An error message "Email cannot be empty" must be shown | An error message "Email cannot be empty" must be shown | Chrome, Firefox, and Edge | High | High | Closed
26 | EC_22 | When I enter a invalid value in Email Field then press tab to move to next field it showed connection error | 1) Enter invalid email in Email field | An error message "Email must be in format example@example.com" must be shown | An error message "Email must be in format example@example.com" must be shown | Chrome, Firefox, and Edge | High | High | Closed
27 | NA_2 | When I enter a character value in Customer ID Field it showed no error | 1) Enter character value in Customer id Field | An error message "Customer id must be numeric" must be shown | An error message "Customer id must be numeric" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
28 | NA_3 | When I enter a special character value in Customer ID Field it showed no error | 1) Enter Special Character In Customer id Field | An error message "Customer id cannot have special character" must be shown | An error message "Customer id cannot have special character" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
29 | NA_4 | When I enter a blank space in Customer ID Field it showed no error | 1) Customer Id cannot have Blank space 2) Press Tab | An error message "Customer id cannot have blank space" must be shown | An error message "Customer id cannot have blank space" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
30 | NA_5 | When I enter a first characther space in Customer ID Field it showed no error | 1) Enter first character space 2) Press Tab | An error message "Customer id cannot have first character space" must be shown | An error message "Customer id cannot have first character space" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
31 | NA_6 | When I don’t enter value in Deposit Field it showed no error | 1) Do not enter a value in Initial Deposit Field 2) Press TAB and move to next Field | An error message "Initial deposit cannot be empty" must be shown | An error message "Initial deposit cannot be empty" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
32 | NA_7 | When I enter character value in Deposit Field it showed no error | 1) Enter character value in Initial Deposit Field | An error message "Initial Deposit must be numeric" must be shown | An error message "Initial Deposit must be numeric" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
33 | NA_8 | When I enter special character value in Deposit Field it showed no error | 1) Enter Special Character In Initial Deposit Field | An error message "Initial Deposit cannot have special character" must be shown | An error message "Initial Deposit cannot have special character" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
34 | NA_9 | When I enter sblank space in Deposit Field it showed no error | 1) Initial Deposit cannot have Blank space 2) Press Tab | An error message "Initial Deposit cannot have blank space" must be shown | An error message "Initial Deposit cannot have blank space" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
35 | NA_10 | When I enter a first characther space in Deposit Field it showed no error | 1) Enter first character space 2) Press Tab | An error message "Initial Deposit cannot have first character space" must be shown | An error message "Initial Deposit cannot have first character space" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
36 | EA_4 | When I enter a valid account number in Edit Account Field it showed no connection error | 1) Enter valid Account Number 2) Submit | Edit Account successfully redirect to Edit Account Form | Edit Account successfully redirect to Edit Account Form | Chrome, Firefox, and Edge | High | High | Closed
37 | EA_7 | When I don’t enter value in Customer ID Field it showed no connection error | 1) Do not enter a value in Customer id Field 2) Press TAB and move to next Field | An error message "Customer id cannot be empty" must be shown | An error message "Customer id cannot be empty" must be shown | Chrome, Firefox, and Edge | High | High | Closed
38 | EA_8 | When I enter value in Customer ID Field it showed no connection error | 1) Enter character value in Customer id Field | An error message "Customer id must be numeric" must be shown | An error message "Customer id must be numeric" must be shown | Chrome, Firefox, and Edge | High | High | Closed
39 | EA_9 | When I enter special character value in Customer ID Field it showed no connection error | 1) Enter Special Character In Customer id Field | An error message "Customer id cannot have special character" must be shown | An error message "Customer id cannot have special character" must be shown | Chrome, Firefox, and Edge | High | High | Closed
40 | EA_10 | When I enter a blank space in Customer ID Field it showed no connection error | 1) Customer Id cannot have Blank space 2) Press Tab | An error message "Customer id cannot have blank space" must be shown | An error message "Customer id cannot have blank space" must be shown | Chrome, Firefox, and Edge | High | High | Closed
41 | EA_11 | When I enter a first character space in Customer ID Field it showed no connection error | 1) Enter first character space 2) Press Tab | An error message "Customer id cannot have first character space" must be shown | An error message "Customer id cannot have first character space" must be shown | Chrome, Firefox, and Edge | High | High | Closed
42 | EA_12 | When I don’t enter value in Balance Field it showed no connection error | 1) Do not enter a value in Balance Field 2) Press TAB and move to next Field | An error message "Balance cannot be empty" must be shown | An error message "Balance cannot be empty" must be shown | Chrome, Firefox, and Edge | High | High | Closed
43 | EA_13 | When I enter a character value in Balance Field it showed no connection error | 1) Enter character value in Balance Field | An error message "Balance must be numeric" must be shown | An error message "Balance must be numeric" must be shown | Chrome, Firefox, and Edge | High | High | Closed
44 | EA_14 | When I enter a special character value in Balance Field it showed no connection error | 1) Enter Special Character In Balance Field | An error message "Balance cannot have special character" must be shown | An error message "Balance cannot have special character" must be shown | Chrome, Firefox, and Edge | High | High | Closed
45 | EA_15 | When I enter a blank space in Balance Field it showed no connection error | 1) Balance cannot have Blank space 2) Press Tab | An error message "Balance cannot have blank space" must be shown | An error message "Balance cannot have blank space" must be shown | Chrome, Firefox, and Edge | High | High | Closed
46 | EA_16 | When I enter a first character space in Balance Field it showed no connection error | 1) Enter first character space 2) Press Tab | An error message "Balance cannot have first character space" must be shown | An error message "Balance cannot have first character space" must be shown | Chrome, Firefox, and Edge | High | High | Closed
47 | DC_4 | When I enter a blank space in Customer ID Field it showed no connection error | 1) Customer ID cannot have Blank space 2) Press Tab | An error message "Customer ID cannot have blank space" must be shown | An error message "Customer ID cannot have blank space" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
48 | DC_5 | When I enter a first character space in Customer ID Field it showed no connection error | 1) Enter first character space 2) Press Tab | An error message "Customer ID cannot have first character space" must be shown | An error message "Customer ID cannot have first character space" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
49 | CS_4 | When I enter a blank space in Account Number Field it showed Character are not allowed | 1) Account no cannot have Blank space 2) Press Tab | An error message "Account no cannot have blank space" must be shown | An error message "Account no cannot have blank space" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
50 | CS_6 | When I don’t enter value in Amount Field it showed no connection error | 1) Do not enter a value in Amount Field 2) Press TAB and move to next Field | An error message "Amount Lower Limit cannot be empty" must be shown | An error message "Amount Lower Limit cannot be empty" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
51 | CS_7 | When I enter lower limit number value in Amount Field it showed no error | 1) Enter numeric value in Amount Lower Limit number Field | An error message "Amount Lower Limit must be numeric" must be shown | An error message "Amount Lower Limit must be numeric" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
52 | CS_8 | When I enter special character value in Amount Field it showed no error | 1) Enter Special Character In Amount Field | An error message "Amount Lower Limit cannot have special character" must be shown | An error message "Amount Lower Limit cannot have special character" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
53 | CS_9 | When I enter a blank space in Amount Number Number Field it showed no error | 1) Amount no cannot have Blank space 2) Press Tab | An error message "Amount Lower Limit cannot have blank space" must be shown | An error message "Amount Lower Limit cannot have blank space" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
54 | CS_10 | When I enter a first character space in Amount Field it showed no error | 1) Enter first character space 2) Press Tab | An error message "Amount Lower Limit cannot have first character space" must be shown | An error message "Amount Lower Limit cannot have first character space" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
55 | CS_11 | When I don’t enter value in Amount Field then press tab it showed no error | 1) Do not enter a value in Number of Transaction Field 2) Press TAB and move to next Field | An error message "Number of Transaction cannot be empty" must be shown | An error message "Number of Transaction cannot be empty" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
56 | CS_12 | When I enter a character value in Number of trasnaction Field it showed no error | 1) Enter character value in Number of Transaction number Field | An error message "Number of Transaction must be numeric" must be shown | An error message "Number of Transaction must be numeric" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
57 | CS_13 | When I enter special character value in Number of transaction Field it showed no error | 1) Enter Special Character In Number for Transaction Field | An error message "Number of Transaction cannot have special character" must be shown | An error message "Number of Transaction cannot have special character" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
58 | CS_14 | When I enter a blank space in Number of transaction Field it showed no error | 1) Number of transaction cannot have Blank space 2) Press Tab | An error message "Number of Transaction cannot have blank space" must be shown | An error message "Number of Transaction cannot have blank space" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
59 | CS_15 | When I enter a first character space in Number of transaction Field then press tab it showed no error | 1) Enter first character space 2) Press Tab | An error message "Number Of Transaction cannot have first character space" must be shown | An error message "Number Of Transaction cannot have first character space" must be shown | Chrome, Firefox, and Edge | Medium | Medium | Closed
60 | IP_1 | When I enter a value of all required fields i then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display "Customer added successfully !!" | Message Should be display "Customer added successfully !!" | Chrome, Firefox, and Edge | High | High | Closed
61 | IP_2 | When I enter a value of all required fields with existed user i then press submit it showed connection error | 1) Enter all required field with existing user data 2) Submit | Message Should be displayed"Email address already exist" | Message Should be displayed"Email address already exist" | Chrome, Firefox, and Edge | High | High | Closed
62 | IP_3 | When I enter a value of all required fields uo update records then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be displayed" customer records updated successfully!!" | Message Should be displayed" customer records updated successfully!!" | Chrome, Firefox, and Edge | High | High | Closed
63 | IP_4 | When I enter a value of all required fields uo update records then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display" customer records updated successfully!!" | Message Should be display" customer records updated successfully!!" | Chrome, Firefox, and Edge | High | High | Closed
64 | IP_5 | When I enter a value of all required fields to update records then press submit it showed connection error | 1) Enter the required fields 2) Submit | Message Should be display" You are not authorise to edit this customer!!" | Message Should be display" You are not authorise to edit this customer!!" | Chrome, Firefox, and Edge | High | High | Closed
65 | IP_6 | When I enter a value of all required fields to generate account then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display " account generated successfully" | Message Should be display " account generated successfully" | Chrome, Firefox, and Edge | High | High | Closed
66 | IP_7 | When I enter a value of all required fields with customer id and then press submit it showed connection error | 1) Enter all fields with customer id and account type already exist | Message Should be display " account generated successfully" | Message Should be display " account generated successfully" | Chrome, Firefox, and Edge | High | High | Closed
67 | IP_8 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter Account Number 2) Submit | Display Generated ministatement | Display Generated ministatement | Chrome, Firefox, and Edge | High | High | Closed
68 | IP_9 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter account number 2) Submit | Message Should be display " account detail successfully updated" | Message Should be display " account detail successfully updated" | Chrome, Firefox, and Edge | High | High | Closed
69 | IP_10 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter all required fields 2) Submit | Display Generated ministatement | Display Generated ministatement | Chrome, Firefox, and Edge | High | High | Closed
70 | IP_11 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display"Account deleted Successfully" | Message Should be display"Account deleted Successfully" | Chrome, Firefox, and Edge | High | High | Closed
71 | IP_12 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display"Account does not exist " | Message Should be display"Account does not exist " | Chrome, Firefox, and Edge | High | High | Closed
72 | IP_13 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display"Account does not exist " | Message Should be display"Account does not exist " | Chrome, Firefox, and Edge | High | High | Closed
73 | IP_14 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1)Enter all required field of deleted account 2)Submit | Message Should be display - "Account does not exist" | Message Should be display - "Account does not exist" | Chrome, Firefox, and Edge | High | High | Closed
74 | IP_15 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter all required fields 2) Submit | Message Should be display"Customer could not be deleted " | Message Should be display"Customer could not be deleted " | Chrome, Firefox, and Edge | High | High | Closed
75 | IP_16 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1)Enter all required field of deleted account 2)Submit | Message Should be display"You are not authorise to delete this account " | Message Should be display"You are not authorise to delete this account " | Chrome, Firefox, and Edge | High | High | Closed
76 | IP_17 | When I enter a account number of all required fields with customer id and then press submit it showed connection error | 1) Enter Account Number 2) Submit | Displayed Generated ministatement | Displayed Generated ministatement | Chrome, Firefox, and Edge | High | High | Closed
77 | IP_18 | when I enter value of all required field then press submit it showed connection error | 1) Enter all required fields 2) Submit | Display Generated Customized statement | Display Generated Customized statement | Chrome, Firefox, and Edge | High | High | Closed
78 | Exploratory Testing | When I check the name of website it showed Gtpl Bank. | Check the Name of the Website | Guru99 Bank | Guru99 Bank | Chrome, Firefox, and Edge | High | Low | Closed

## Defects_v3
Bug Report Template
Project Name |  |  | Banking System |  |  | Manual Testing
Raised By |  |  | Seif Aldin Yasser
Assigned to |  |  | Development Team
Software Version |  |  | V3
Date |  |  | 15/10/2024
Defect_ID | Test Case_ID | Summary | Steps to Reproduce | Expected result | Actual Result | Enviroment | Eviedence | Priority | Severity | Status
1 | SM_6 | When I click on delete account then enter an account number it is showed "This page isnt working". | 1) Click on Delete Account 2) Enter required fields 3) Submit | 1) A pop - up "Do you really want to delete this account?" | This page isnt working | Chrome, Firefox, and Edge |  | Low | Low | Open
2 | SM_11 | When I click on delete customer then enter a customer id it is showed "This page isnt working". | 1) Click on Delete Customer 2) Enter Customer id 3) Submit | 1) A pop up "Do you really want to delete this customer?" | This page isnt working | Chrome, Firefox, and Edge |  | Low | Low | Open
3 | SM_14 | When I click on edit customer then enter a customer id it is showed alert "You are not authorise to edit this customer!!". | 1) Click on Edit Customer 2) Enter Customer id 3) Submit | 1)A pop - up "Customer does not exist" 2) Redirect to Delete customer | alert " You are not authorise to edit this customer!!" redirect to delete customer page | Chrome, Firefox, and Edge |  | Low | Low | Open
4 | SM_15 | When I click on delete customer then enter a customer id it is showed alert "You are not authorise to edit this customer!!". | 1) Click on Delete Customer 2) Enter Customer id 3) Submit | 1)A pop - up "Customer does not exist" 2) Redirects to Delete Customer | alert " You are not authorise to delete this customer!!" redirect to delete customer page | Chrome, Firefox, and Edge |  | Low | Low | Open
5 | SM_21 | When I click on fund transfer then enter an (amount, same from account number, to same account number, and description) it is showed transfer sucessful and displayed data. | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | 1) A pop up "Payers account No and Payees account No Must Not be Same!!!" | Transfer sucessful and displayed data. | Chrome, Firefox, and Edge |  | Medium | Low | Open
6 | SM_28 | When I click on withdrawal then enter a all required fields it is showed "This page isnt working". | 1)Click on Withdrawal 2) Enter all required fields 3) Submit | An Error message "Transaction failed account balance is low !!" | This page isnt working | Chrome, Firefox, and Edge |  | Medium | Low | Open
7 | SC_5 | When I click on balance enquiry then enter worng account number which it not associated with customer it is showed "This page isnt working". | 1) Click on Balance enquiry 2) Enter wrong account number which is not associated with customer 3) Submit | Display alert message " You are not authorize to get Balance details of this account!! " | This page isnt working | Chrome, Firefox, and Edge |  | Medium | Low | Open
8 | SC_18 | When I click on customize statement then enter all required fields it is showed alert "Account does not exist". | 1) Click on customize statement 2) Enter all required fields 3) Submit | Display alert messsage " FromDate field should be lower than ToDate field!!" | Display alert messsage " Account does not exist " | Chrome, Firefox, and Edge |  | High | Medium | Open

## Defects_v4
Bug Report Template
Project Name |  |  | Banking System |  |  | Manual Testing
Raised By |  |  | Seif Aldin Yasser
Assigned to |  |  | Development Team
Software Version |  |  | V4
Date |  |  | 16/10/2024
Defect_ID | Test Case_ID | Summary | Steps to Reproduce | Expected result | Actual Result | Enviroment | Priority | Severity | Status
1 | NC_4 | When I enter a First character blank space in Name Field it showed Number are not allowed | 1) Enter First character Blank space | 1) A pop - up "Do you really want to delete this account?" | 1) A pop - up "Do you really want to delete this account?" | Chrome, Firefox, and Edge | Low | Low | Closed
2 | NC_5 | When I don’t enter a value in address field it is not showed any error messages | 1) Do not enter a value in ADDRESS Field 2) Press TAB and move to next Field | 1) A pop up "Do you really want to delete this customer?" | 1) A pop up "Do you really want to delete this customer?" | Chrome, Firefox, and Edge | Low | Low | Closed
3 | NC_6 | When I enter a First character blank space in Address Field it is not showed any error messages | 1) Enter First character Blank space | 1)A pop - up "Customer does not exist" 2) Redirect to Delete customer | 1)A pop - up "Customer does not exist" 2) Redirect to Delete customer | Chrome, Firefox, and Edge | Low | Low | Closed
4 | NC_7 | When I enter a First character blank space in City Field it showed Number are not allowed | 1) Enter First character Blank space | 1)A pop - up "Customer does not exist" 2) Redirects to Delete Customer | 1)A pop - up "Customer does not exist" 2) Redirects to Delete Customer | Chrome, Firefox, and Edge | Low | Low | Closed
5 | NC_11 | When I enter a First character blank space in State Field it showed Number are not allowed | 1) Enter First character Blank space | 1) A pop up "Payers account No and Payees account No Must Not be Same!!!" | 1) A pop up "Payers account No and Payees account No Must Not be Same!!!" | Chrome, Firefox, and Edge | Medium | Low | Closed
6 | NC_20 | When I enter a First character blank space in Pin Field it showed Number are not allowed | 1) Enter First character Blank space | An Error message "Transaction failed account balance is low !!" | An Error message "Transaction failed account balance is low !!" | Chrome, Firefox, and Edge | Medium | Low | Closed
7 | NC_23 | When I enter a First character blank space in Telephone Field it showed Number are not allowed | 1) Enter First character Blank space | Display alert message " You are not authorize to get Balance details of this account!! " | Display alert message " You are not authorize to get Balance details of this account!! " | Chrome, Firefox, and Edge | Medium | Low | Closed
8 | EC_4 | When I enter a valid Cutomer id and press submit it showed connection error | 1) Enter valid Customer id 2) Submit | Display alert messsage " FromDate field should be lower than ToDate field!!" | Display alert messsage " FromDate field should be lower than ToDate field!!" | Chrome, Firefox, and Edge | High | Medium | Closed

## Status (hidden)
PASS
FAIL
N/A
N/E