## Change Log
Change Log
Project Name | Banking System | Manual Testing
By | Seif Aldin Yasser
Change Version | Date | Description
1 | 2024-10-10 | 1) Initial Draft
1.1 | 2024-11-10 | 1) Added Test Steps and Test Data
1.2 | 2024-12-10 | 1) Test case executed. 2) Test result updated.
1.3 | 13/10/2024 | 1) Changed Amount lower limit field to Minimum Transaction Value as per SRS version 2. 2) Deleted test cases EA7 to EA16 in Edit Account as per changes in the SRS_v2. 3) Deleted Test Cases EC5, EC6, EC7, EC9 as per changes in module Edit Customer in SRS_v2.
1.4 | 14/10/2024 | 1) Retesting done on v2 of website. 2) Test result updated.
2 | 15/10/2024 | Test cases SC5, SC6 are deleted as per SRSv4
2.1 | 16/10/2024 | Retested on SRSv4 and results updated

## Test Case
Test Cases Document
Project Name |  | Banking System |  |  |  | Manual Testing
Tester Name |  | Seif Aldin Yasser
Software Version |  | V2.1
Date |  | 16/10/2024
ID | Test Scenario | Test Case | Test Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Retesting in V2.1 | Status
NC_1 | Verify Name Field Functionality | Check Name cannot be empty | The Screen of New Customer is Opened | 1) Do not enter a value in NAME Field 2) Press TAB and move to next Field | No Input Data | An error message "Customer name must not be blank" must shown | An error message "Customer name must not be blank" is shown | No Change | Pass
NC_2 |  | Check Name cannot be numeric | The Screen of New Customer is Opened | 1) Enter numeric value in NAME Field 2) Press TAB and move to next Field | Name:1234 Name: name123 | An error message "Numbers are not allowed" must be shown | An error message "Numbers are not allowed" is shown | No Change | Pass
NC_3 |  | Check Name cannot have special characters | The Screen of New Customer is Opened | 1) Enter Special Character In NAME Field 2) Press TAB and move to next Field | Name:name!@# Name: !@# | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" is shown | No Change | Pass
NC_4 |  | Check Name cannot have first character as blank space | The Screen of New Customer is Opened | 1) Enter First character Blank space 2) Press TAB and move to next Field | No Input Data | An error message "First character cannot have space" must be shown | An error message "Numbers are not allowed" is shown | An error message "First character cannot have space" is shown | Pass
NC_5 | Verify Address Field Functionality | Check Address cannot be empty | The Screen of New Customer is Opened | 1) Do not enter a value in ADDRESS Field 2) Press TAB and move to next Field | No Input Data | An error message "ADDRESS Field must not be blank" must be shown | No error message is shown | An error message "ADDRESS Field must not be blank" is shown | Pass
NC_6 |  | Check Address cannot have first blank space | The Screen of New Customer is Opened | 1) Enter First character Blank space 2) Press TAB and move to next Field | No Input Data | An error message "First character cannot have space" must be shown | No error message is shown | An error message "First character cannot have space" is shown | Pass
NC_7 | Verify City Field Functionality | Check City cannot be empty | The Screen of New Customer is Opened | 1) Do not enter a value in CITY Field 2) Press TAB and move to next Field | No Input Data | An error message "City Field must be not blank" must be shown | An error message "City Field must be not blank" is shown | No Change | Pass
NC_8 |  | Check City cannot be numeric | The Screen of New Customer is Opened | 1) Enter numeric value in CITY Field 2) Press TAB and move to next Field | City: 1234 City: city123 | An error message "Numbers are not allowed" must be shown | An error message "Numbers are not allowed" is shown | No Change | Pass
NC_9 |  | Check City cannot have special character | The Screen of New Customer is Opened | 1) Enter Special Character In CITY Field 2) Press TAB and move to next Field | City: City!@# City: !@# | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" is shown | No Change | Pass
NC_10 |  | Check City cannot have first blank space | The Screen of New Customer is Opened | 1) Enter First character Blank space 2) Press TAB and move to next Field | No Input Data | An error message "First character cannot have space" must be shown | An error message "Numbers are not allowed" is shown | An error message "First character cannot have space" is shown | Pass
NC_11 | Verify State Field Functionality | Check State cannot be empty | The Screen of New Customer is Opened | 1) Do not enter a value in STATE Field 2) Press TAB and move to next Field | No Input Data | An error message "State must not be blank" must be shown | An error message "State must not be blank" is shown | No Change | Pass
NC_12 |  | Check State cannot be numeric | The Screen of New Customer is Opened | 1) Enter numeric value in STATE Field 2) Press TAB and move to next Field | State: 1234 State: State123 | An error message "Numbers are not allowed" must be shown | An error message "Numbers are not allowed" is shown | No Change | Pass
NC_13 |  | Check State cannot have special character | The Screen of New Customer is Opened | 1) Enter Special Character In STATE Field 2) Press TAB and move to next Field | State: State!@# State: !@# | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" is shown | No Change | Pass
NC_14 |  | Check State cannot have first blank space | The Screen of New Customer is Opened | 1) Enter First character Blank space 2) Press TAB and move to next Field | No Input Data | An error message "First character cannot have space" must be shown | An error message "Numbers are not allowed" is shown | An error message "First character cannot have space" is shown | Pass
NC_15 | Verify PIN Field Functionality | Check PIN must be numeric | The Screen of New Customer is Opened | 1) Enter character value in PIN Field 2) Press TAB and move to next Field | Pin: 1234 Pin: 1234PIN | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" is shown | No Change | Pass
NC_16 |  | Check PIN cannot be empty | The Screen of New Customer is Opened | 1) Do not enter a value in PIN Field 2) Press TAB and move to next Field | No Input Data | An error message "PIN code must not be blank" must be shown | An error message "PIN code must not be blank" is shown | No Change | Pass
NC_17 |  | Check PIN must have 6 digits | The Screen of New Customer is Opened | 1) Enter More than 6 digit in PIN field 2) Enter Less Than 6 digit in PIN field 3) Press TAB and move to next Field | Pin: 12 Pin: 123 | An error message "PIN Code must have 6 Digits" must be shown | An error message "PIN Code must have 6 Digits" is shown | No Change | Pass
NC_18 |  | Check PIN cannot have special character | The Screen of New Customer is Opened | 1) Enter Special Character In PIN Field 2) Press TAB and move to next Field | Pin: !@# Pin: 123!@# | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" is shown | No Change | Pass
NC_19 |  | Check PIN cannot have first blank space | The Screen of New Customer is Opened | 1) Enter First character Blank space 2) Press TAB and move to next Field | No Input Data | An error message "First character cannot have space" must be shown | An error message "Characters are not allowed" is shown | An error message "First character cannot have space" is shown | Pass
NC_20 |  | Check PIN cannot have blank space | The Screen of New Customer is Opened | 1) Enter First character Blank space 2) Press TAB and move to next Field | No Input Data | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" is shown | An error message "Characters are not allowed" is shown | Pass
NC_21 | Verify Telephone Field Functionality | Check Telephone cannot be empty | The Screen of New Customer is Opened | 1) Do not enter a value in Telephone Field 2) Press TAB and move to next Field | No Input Data | An error message "Telephone no must not be blank" must be shown | An error message "Telephone no must not be blank" is shown | No Change | Pass
NC_22 |  | Check Telephone cannot have first character as blank space | The Screen of New Customer is Opened | 1) Enter First character Blank space 2) Press TAB and move to next Field | No Input Data | An error message "First character cannot have space" must be shown | An error message "Characters are not allowed" is shown | An error message "First character cannot have space" is shown | Pass
NC_23 |  | Check Telephone cannot have spaces | The Screen of New Customer is Opened | 1) Enter Blank space in Telephone 2) Press TAB and move to next Field | Telephone: 123 123 | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" is shown | An error message "Characters are not allowed" is shown | Pass
NC_24 |  | Check Telephone cannot have special character | The Screen of New Customer is Opened | 1) Enter Special Character In Telephone Field 2) Press TAB and move to next Field | Telephone: 886636!@12 Telephone: !@88662682 Telephone: 88663682!@ | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" is shown | No Change | Pass
NC_25 | Verify Email Field Functionality | Check Email cannot be empty | The Screen of New Customer is Opened | 1) Do not enter a value in Email Field 2) Press TAB and move to next Field | No Input Data | An error message "Email ID must not be blank" must be shown | An error message "Email ID must not be blank" is shown | No Change | Pass
NC_26 |  | Check Email must be in correct format | The Screen of New Customer is Opened | 1) Enter invalid email in Email field 2) Press TAB and move to next Field | Email:guru99@gmail Email: guru99 Email:Guru99@ Email: guru99@gmail. Email: guru99gmail.com | An error message "Email-ID is not valid"" must be shown | An error message "Email-ID is not valid"" is shown | No Change | Pass
NC_27 |  | Check Email cannot have space | The Screen of New Customer is Opened | 1) Enter Blank space in Email 2) Press TAB and move to next Field | No Input Data | An error message "Email-ID is not valid" must be shown | An error message "Email-ID is not valid" must be shown | No Change | Pass
NC_28 | Verify Field Labels Functionality | Check Check all Fields name(Label) are as documented in SRS for all modules | The SRS Document is Opened | 1) Check Field names with that in SRS | No Input Data | Field names in SRS and system should match | telephone number will be "Mobile number" | Telephone number field renamed as Mobile Number | Pass
EC_1 | Verify Customer id Functionality | Check Customer id cannot be empty | The Screen of Edit Customer is Opened | 1) Do not enter a value in Customer id Field 2) Press TAB and move to next Field | No Input Data | An error message "Customer ID is required" must be shown | An error message "Customer ID is required" is shown | No Change | Pass
EC_2 |  | Check Customer id must be numeric | The Screen of Edit Customer is Opened | 1) Enter character value in Customer id Field 2) Press TAB and move to next Field | Customer ID:1234Acc Customer ID: Acc123 | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" is shown | No Change | Pass
EC_3 |  | Check Customer id cannot have special character | The Screen of Edit Customer is Opened | 1) Enter Special Character In Customer id Field 2) Press TAB and move to next Field | Customer ID:123!@# Customer ID: !@# | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" is shown | No Change | Pass
EC_4 |  | Check Validation of Customer Id | The Screen of Edit Customer is Opened | 1) Enter valid Customer id 2) Submit | Customer ID:XYZ | Edit Customer successfully redirect to Edit Customer Page | Connection Error is shown " Warning: mysql_connect() [function.mysql-connect]: Access denied for user 'root'@'localhost' (using password: NO) in /home/demo/public_html/V1/html/editCustomerPage.php on line 3 could not connect Access denied for user 'root'@'localhost' (using password: NO) " | Edit Customer successfully redirect to Edit Customer Page | Pass
EC_8 | Verify Address Field Functionality | Check Address cannot be empty | The Screen of Edit Customer is Opened | 1) Do not enter a value in ADDRESS Field 2) Press TAB and move to next Field | No Input Data | An error message "Address Field must not be blank" must be shown | Cannot be executed due to connection issue | An error message "Address Field must not be blank" is shown | Pass
EC_10 | Verify City Field Functionality | Check City cannot be empty | The Screen of Edit Customer is Opened | 1) Do not enter a value in CITY Field 2) Press TAB and move to next Field | No Input Data | An error message "City Field must not be blank" must be shown | Cannot be executed due to connection issue | An error message "City Field must not be blank" is shown | Pass
EC_11 |  | Check City cannot be numeric | The Screen of Edit Customer is Opened | 1) Enter numeric value in CITY Field 2) Press TAB and move to next Field | City: 1234 City: city123 | An error message "Numbers are not allowed" must be shown | Cannot be executed due to connection issue | An error message "Numbers are not allowed" is shown | Pass
EC_12 |  | Check City cannot have special character | The Screen of Edit Customer is Opened | 1) Enter Special Character In CITY Field 2) Press TAB and move to next Field | City: City!@# City: !@# | An error message "Special characters are not allowed" must be shown | Cannot be executed due to connection issue | An error message "Special characters are not allowed" is shown | Pass
EC_13 | Verify State Field Functionality | Check State cannot be empty | The Screen of Edit Customer is Opened | 1) Do not enter a value in STATE Field 2) Press TAB and move to next Field | No Input Data | An error message "State must not be blank" must be shown | Cannot be executed due to connection issue | An error message "State must not be blank" is shown | Pass
EC_14 |  | Check State cannot be numeric | The Screen of Edit Customer is Opened | 1) Enter numeric value in STATE Field 2) Press TAB and move to next Field | State: 1234 State: State123 | An error message "Numbers are not allowed" must be shown | Cannot be executed due to connection issue | An error message "Numbers are not allowed" is shown | Pass
EC_15 |  | Check State cannot have special character | The Screen of Edit Customer is Opened | 1) Enter Special Character In STATE Field 2) Press TAB and move to next Field | State: State!@# State: !@# | An error message "Special characters are not allowed" must be shown | Cannot be executed due to connection issue | An error message "Special characters are not allowed" is shown | Pass
EC_16 | Verify PIN Field Functionality | Check PIN must be numeric | The Screen of Edit Customer is Opened | 1) Enter character value in PIN Field 2) Press TAB and move to next Field | Pin: 1234 Pin: 1234PIN | An error message "Characters are not allowed" must be shown | Cannot be executed due to connection issue | An error message "Characters are not allowed" is shown | Pass
EC_17 |  | Check PIN cannot be empty | The Screen of Edit Customer is Opened | 1) Do not enter a value in PIN Field 2) Press TAB and move to next Field | No Input Data | An error message "PIN Code must not be blank" must be shown | Cannot be executed due to connection issue | An error message "PIN Code must not be blank" is shown | Pass
EC_18 |  | Check PIN must have 6 digits | The Screen of Edit Customer is Opened | 1) Enter More than 6 digit in PIN field 2) Enter Less Than 6 digit in PIN field 3) Press TAB and move to next Field | Pin: 1234567 Pin: 123 | An error message "PIN Code must have 6 Digits" must be shown | Cannot be executed due to connection issue | An error message "PIN Code must have 6 Digits" is shown | Pass
EC_19 |  | Check PIN cannot have special character | The Screen of Edit Customer is Opened | 1) Enter Special Character In PIN Field 2) Press TAB and move to next Field | Pin: !@# Pin: 123!@# | An error message "Special characters are not allowed" must be shown | Cannot be executed due to connection issue | An error message "Special characters are not allowed" is shown | Pass
EC_20 | Verify Telephone Field Functionality | Check Telephone cannot be empty | The Screen of Edit Customer is Opened | 1) Do not enter a value in Telephone Field 2) Press TAB and move to next Field | No Input Data | An error message "Mobile no must not be blank" must be shown | Cannot be executed due to connection issue | An error message "Mobile no must not be blank" is shown | Pass
EC_21 |  | Check Telephone cannot have special character | The Screen of Edit Customer is Opened | 1) Enter Special Character In PIN Field 2) Press TAB and move to next Field | Telephone: 886636!@12 Telephone: !@88662682 Telephone: 88663682!@ | An error message "Special characters are not allowed" must be shown | Cannot be executed due to connection issue | An error message "Special characters are not allowed" is shown | Pass
EC_22 | Verify Email Field Functionality | Check Email cannot be empty | The Screen of Edit Customer is Opened | 1) Do not enter a value in Email Field 2) Press TAB and move to next Field | No Input Data | An error message "Email-ID must not be blank" must be shown | Cannot be executed due to connection issue | An error message "Email-ID must not be blank" is shown | Pass
EC_23 |  | Check Email must be in format career@guru99.com | The Screen of Edit Customer is Opened | 1) Enter invalid email in Email field 2) Press TAB and move to next Field | Email: guru99@gmail Email: guru99 Email: Guru99@ Email:gurugmail.com | An error message "Email-ID is not valid" must be shown | Cannot be executed due to connection issue | An error message "Email-ID is not valid" is shown | Pass
NA_1 | Verify Customer id Functionality | Check Customer id cannot be empty | The Screen of New Account is Opened | 1) Do not enter a value in Customer id Field 2) Press TAB and move to next Field | No Input Data | An error message "Customer ID is required" must be shown | No error message is shown | An error message "Customer ID is required" is shown | Pass
NA_2 |  | Check Customer id must be numeric | The Screen of New Account is Opened | 1) Enter character value in Customer id Field 2) Press TAB and move to next Field | Customer ID: 1234Acc Customer ID: Acc123 | An error message "Characters are not allowed" must be shown | No error message is shown | An error message "Characters are not allowed" is shown | Pass
NA_3 |  | Check Customer id cannot have special character | The Screen of New Account is Opened | 1) Enter Special Character In Customer id Field 2) Press TAB and move to next Field | Customer ID: 123!@# Customer ID: !@# | An error message "Special characters are not allowed" must be shown | No error message is shown | An error message "Special characters are not allowed" is shown | Pass
NA_4 |  | Check Customer id cannot have blank space | The Screen of New Account is Opened | 1) Customer Id cannot have Blank space 2) Press TAB and move to next Field | Customer ID: 123 12 | An error message "Characters are not allowed" must be shown | No error message is shown | An error message "Characters are not allowed" is shown | Pass
NA_5 |  | Check First Character cannot be space | The Screen of New Account is Opened | 1) Enter first character space 2) Press TAB and move to next Field | No Input Data | An error message "First character cannot have space" must be shown | No error message is shown | An error message "First character cannot have space" is shown | Pass
NA_6 | Verify Initial Deposit Functionality | Check Initial Deposit Cannot be empty | The Screen of New Account is Opened | 1) Do not enter a value in Initial Deposit Field 2) Press TAB and move to next Field | No Input Data | An error message "Initial Deposit must not be blank" must be shown | No error message is shown | An error message "Initial Deposit must not be blank" is shown | Pass
NA_7 |  | Check Initial Deposit Must be numeric | The Screen of New Account is Opened | 1) Enter character value in Initial Deposit Field 2) Press TAB and move to next Field | Intial Deposit: 1234Acc Intial Deposit: Acc123 | An error message "Characters are not allowed" must be shown | No error message is shown | An error message "Special characters are not allowed" must be shown | Pass
NA_8 |  | Check Initial Deposit Cannot have special character | The Screen of New Account is Opened | 1) Enter Special Character In Initial Deposit Field 2) Press TAB and move to next Field | Intial Deposit: 123!@# Intial Deposit: !@# | An error message "Special characters are not allowed" must be shown | No error message is shown | An error message "Special characters are not allowed" is shown | Pass
NA_9 |  | Check Initial Deposit cannot have blank space | The Screen of New Account is Opened | 1) Initial Deposit cannot have Blank space 2) Press TAB and move to next Field | Intial Deposit: 123 12 | An error message "Special characters are not allowed" must be shown | No error message is shown | An error message "Special characters are not allowed" is shown | Pass
NA_10 |  | Check Initial Deposit First Character cannot be space | The Screen of New Account is Opened | 1) Enter first character space 2) Press TAB and move to next Field | No Input Data | An error message "First character cannot have space" must be shown | No error message is shown | An error message "First character cannot have space" is shown | Pass
EA_1 | Verify account number Functionality | Check The Account number cannot be empty | The Screen of Edit Account is Opened | 1) Do not enter a value in Account number Field 2) Press TAB and move to next Field | No Input Data | An error message "Account Number must not be blank" must be shown | An error message "Account Number must not be blank" is shown | No Change | Pass
EA_2 |  | Check The Account number must be numeric | The Screen of Edit Account is Opened | 1) Enter character value in Account number Field 2) Press TAB and move to next Field | Account Number: 1234 Account Number: Acc123 | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" must be shown | No Change | Pass
EA_3 |  | Check The Account number cannot have special character | The Screen of Edit Account is Opened | 1) Enter Special Character In Account number Field 2) Press TAB and move to next Field | Account Number: 123!@# Account Number: !@# | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" is shown | No Change | Pass
EA_4 |  | Check The Valid Account Number | The Screen of Edit Account is Opened | 1) Enter valid Account Number 2) Submit | Account Number: 128 | Edit Account successfully redirect to Edit Account Form | Connection Error is shown " Warning: mysql_connect() [function.mysql-connect]: Access denied for user 'root'@'localhost' (using password: NO) in /home/demo/public_html/V1/html/editCustomerPage.php on line 3 could not connect Access denied for user 'root'@'localhost' (using password: NO) " | Edit Account successfully redirect to Edit Account Form | Pass
EA_5 |  | Check The Account number cannot have blank space | The Screen of Edit Account is Opened | 1) Account no cannot have Blank space 2) Press TAB and move to next Field | Account Number: 123 12 | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" must be shown | No Change | Pass
EA_6 |  | Check The First Character cannot be space | The Screen of Edit Account is Opened | 1) Enter first character space 2) Press TAB and move to next Field | No Input Data | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" is shown | No Change | Pass
EA_7 | Verify the Change of account type Functionality | Check The Change saving account to current account | The Screen of Edit Account is Opened | 1)Select current from Drop down 2)Press Submit | No Input Data | A Message display " account details updated successfully " | can not be executed | A Message displayed " account details updated successfully " | Pass
EA_8 |  | Check The Change Current account to Savings account | The Screen of Edit Account is Opened | 1)Select current from Drop down 2)Press Submit | No Input Data | A Message display " account details updated successfully " | can not be executed | A Message displayed " account details updated successfully " | Pass
DA_1 | Verify account number Functionality | Check Account number cannot be empty | The Screen of Delete Account is Opened | 1) Do not enter a value in Account number Field 2) Press TAB and move to next Field | No Input Data | An error message "Account Number must not be blank" must be shown | An error message "Account Number must not be blank" must be shown | No Change | Pass
DA_2 |  | Check Account number must be numeric | The Screen of Delete Account is Opened | 1) Enter character value in Account number Field 2) Press TAB and move to next Field | Account Number:1234 Account Number: Acc123 | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" must be shown | No Change | Pass
DA_3 |  | Check Account number cannot have special character | The Screen of Delete Account is Opened | 1) Enter Special Character In Account number Field 2) Press TAB and move to next Field | Account Number:123!@# Account Number: !@# | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" must be shown | No Change | Pass
DA_4 |  | Check Account number cannot have blank space | The Screen of Delete Account is Opened | 1) Account no cannot have Blank space 2) Press TAB and move to next Field | Account Number:123 12 | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" must be shown | No Change | Pass
DA_5 |  | Check First Character cannot be space | The Screen of Delete Account is Opened | 1) Enter first character space 2) Press TAB and move to next Field | No Input Data | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" must be shown | No Change | Pass
DC_1 | Verify Customer ID Functionality | Check Customer ID cannot be empty | The Screen of Delete Customer is Opened | 1) Do not enter a value in Customer ID Field 2) Press TAB and move to next Field | No Input Data | An error message "Customer ID is required" must be shown | An error message "Customer ID is required" must be shown | No Change | Pass
DC_2 |  | Check Customer ID must be numeric | The Screen of Delete Customer is Opened | 1) Enter Character value in Customer ID Field 2) Press TAB and move to next Field | Customer ID: 1234 Customer ID: Acc123 | An error message" Customer ID must be numeric" must be shown | No error message is shown | An error message "Characters are not allowed" must be shown | Pass
DC_3 |  | Check Customer ID cannot have special character | The Screen of Delete Customer is Opened | 1) Enter Special Character In Customer ID Field 2) Press TAB and move to next Field | Customer ID: 123!@# Customer ID: !@# | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" must be shown | No Change | Pass
DC_4 |  | Check Customer ID cannot have blank space | The Screen of Delete Customer is Opened | 1) Customer ID cannot have Blank space 2) Press TAB and move to next Field | Customer ID: 123 12 | An error message "Customer ID cannot have blank space" must be shown | No error message is shown | An error message "Characters are not allowed" must be shown | Pass
DC_5 |  | Check First Character cannot be space | The Screen of Delete Customer is Opened | 1) Enter first character space 2) Press TAB and move to next Field | No Input Data | An error message "Customer ID cannot have first character space" must be shown | No error message is shown | An error message "Characters are not allowed" must be shown | Pass
MS_1 | Verify account number Functionality | Check Account number cannot be empty | The Screen of Mini Statement is Opened | 1) Do not enter a value in Account number Field 2) Press TAB and move to next Field | No Input Data | An error message "Account Number must not be blank" must be shown | An error message "Account Number must not be blank" must be shown | No Change | Pass
MS_2 |  | Check Account number must be numeric | The Screen of Mini Statement is Opened | 1) Enter character value in Account number Field 2) Press TAB and move to next Field | Mini Statement: 1234 Mini Statement: Acc123 | An error message "Characters are not allowed " must be shown | An error message "Characters are not allowed " must be shown | No Change | Pass
MS_3 |  | Check Account number cannot have special character | The Screen of Mini Statement is Opened | 1) Enter Special Character In Account number Field 2) Press TAB and move to next Field | Mini Statement: 123!@# Mini Statement: !@# | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" must be shown | No Change | Pass
MS_4 |  | Check Account number cannot have blank space | The Screen of Mini Statement is Opened | 1) Account no cannot have Blank space 2) Press TAB and move to next Field | Mini Statement: 123 12 | An error message "Characters are not allowed " must be shown | An error message "Characters are not allowed " must be shown | No Change | Pass
MS_5 |  | Check First Character cannot be space | The Screen of Mini Statement is Opened | 1) Enter first character space 2) Press TAB and move to next Field | No Input Data | An error message "Characters are not allowed " must be shown | An error message "Characters are not allowed " must be shown | No Change | Pass
CS_1 | Verify account number Functionality | Check Account number cannot be empty | The Screen of Customized Statement is Opened | 1) Do not enter a value in Account number Field 2) Press TAB and move to next Field | No Input Data | An error message "Account Number must not be blank" must be shown | An error message "Account Number must not be blank" must be shown | No Change | Pass
CS_2 |  | Check Account number must be numeric | The Screen of Customized Statement is Opened | 1) Enter numeric value in Account number Field 2) Press TAB and move to next Field | Account Number: 1234 Account Number: Acc123 | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" must be shown | No Change | Pass
CS_3 |  | Check Account number cannot have special character | The Screen of Customized Statement is Opened | 1) Enter Special Character In Account number Field | Account Number: 123!@# Account Number: !@# | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" must be shown | No Change | Pass
CS_4 |  | Check Account number cannot have blank space | The Screen of Customized Statement is Opened | 1) Account no cannot have Blank space 2) Press TAB and move to next Field | Account Number: 123 12 | An error message "Account no cannot have blank space" must be shown | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" is shown | Pass
CS_5 |  | Check First Character cannot be space | The Screen of Customized Statement is Opened | 1) Enter first character space 2) Press TAB and move to next Field | No Input Data | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" must be shown | No Change | Pass
CS_6 | Verify Amount lower limit Functionality | Check Amount cannot be empty | The Screen of Customized Statement is Opened | 1) Do not enter a value in Amount Field 2) Press TAB and move to next Field | No Input Data | An error message "Amount Lower Limit cannot be empty" must be shown | No error message is shown | An error message "Characters are not allowed" is shown | Pass
CS_7 |  | Check Amount must be numeric | The Screen of Customized Statement is Opened | 1) Enter numeric value in Amount Lower Limit number Field 2) Press TAB and move to next Field | Account Lower Limit: 1234 Account Lower Limit: Acc123 | An error message "Amount Lower Limit must be numeric" must be shown | No error message is shown | An error message "Special characters are not allowed" is shown | Pass
CS_8 |  | Check Amount cannot have special character | The Screen of Customized Statement is Opened | 1) Enter Special Character In Amount Field 2) Press TAB and move to next Field | Account Lower Limit: 123!@# Account Lower Limit: !@# | An error message "Amount Lower Limit cannot have special character" must be shown | No error message is shown | An error message "Characters are not allowed" is shown | Pass
CS_9 |  | Check Amount cannot have blank space | The Screen of Customized Statement is Opened | 1) Amount no cannot have Blank space 2) Press TAB and move to next Field | Account Lower Limit: 123 12 | An error message "Amount Lower Limit cannot have blank space" must be shown | No error message is shown | An error message "Characters are not allowed" is shown | Pass
CS_10 |  | Check First Character cannot be space | The Screen of Customized Statement is Opened | 1) Enter first character space 2) Press TAB and move to next Field | No Input Data | An error message "Amount Lower Limit cannot have first character space" must be shown | No error message is shown | An error message "Characters are not allowed" is shown | Pass
CS_11 | Verify Number of Transaction Functionality | Check Number of transaction cannot be empty | The Screen of Customized Statement is Opened | 1) Do not enter a value in Number of Transaction Field 2) Press TAB and move to next Field | No Input Data | An error message "Number of Transaction cannot be empty" must be shown | No error message is shown | An error message "Special characters are not allowed" is shown | Pass
CS_12 |  | Check Number of transaction must be numeric | The Screen of Customized Statement is Opened | 1) Enter character value in Number of Transaction number Field 2) Press TAB and move to next Field | Number of Transaction: 1234 Number of Transaction: Acc123 | An error message "Number of Transaction must be numeric" must be shown | No error message is shown | An error message "Characters are not allowed" is shown | Pass
CS_13 |  | Check Number of transaction have special character | The Screen of Customized Statement is Opened | 1) Enter Special Character In Number for Transaction Field 2) Press TAB and move to next Field | Number of Transaction: 123!@# Number of Transaction: !@# | An error message "Number of Transaction cannot have special character" must be shown | No error message is shown | An error message "Characters are not allowed" is shown | Pass
CS_14 |  | Check Number of transaction cannot have blank space | The Screen of Customized Statement is Opened | 1) Number of transaction cannot have Blank space 2) Press TAB and move to next Field | Number of Transaction: 123 12 | An error message "Number of Transaction cannot have blank space" must be shown | No error message is shown | An error message "Characters are not allowed" is shown | Pass
CS_15 |  | Check First Character cannot be space | The Screen of Customized Statement is Opened | 1) Enter first character space 2) Press TAB and move to next Field | No Input Data | An error message "Number Of Transaction cannot have first character space" must be shown | No error message is shown | An error message "Characters are not allowed" is shown | Pass
BE_1 | Verify account number Functionality | Check Account number cannot be empty | The Screen of Balance Enquiry is Opened | 1) Do not enter a value in Account number Field 2) Press TAB and move to next Field | No Input Data | An error message "Account Number must not be blank" must be shown | An error message "Account Number must not be blank" is shown | No Change | Pass
BE_2 |  | Check Account number must be numeric | The Screen of Balance Enquiry is Opened | 1) Enter Character value in Account number Field 2) Press TAB and move to next Field | Account Number: 1234 Account Number: Acc123 | An error message "Characters are not allowed" must be shown | An error message "Characters are not allowed" is shown | No Change | Pass
BE_3 |  | Check Account number cannot have special character | The Screen of Balance Enquiry is Opened | 1) Enter Special Character In Account number Field 2) Press TAB and move to next Field | Account Number: 123!@# Account Number: !@# | An error message "Special characters are not allowed" must be shown | An error message "Special characters are not allowed" is shown | No Change | Pass
SM_1 | Verify Change Password and Login Functionality | Check incorrect Old Password | The User Existed in Database | 1) Click on Change Password 2) Enter required fields 3) Submit | Old Password - Incorrect Old Password New password - 123456 Confirm Password - 123456 | 1) A pop-up "Old password is incorrect" is shown 2) User redirected to Change Password | 1) A pop-up "Old password is incorrect" is shown 2) User redirect to Change Password is shown | No Change | Pass
SM_2 |  | Check after password is changed page is redirected to Login screen | The User Existed in Database | 1) Click on Change Password 2) Enter required fields 3) Submit | Old Password - correct Old Password New password - 123456 Confirm Password - 123456 | 1) A pop-up "Password is changed" is shown 2) User logged out and redirected to login page | 1) A pop-up "Password is changed" is shown 2) User logged out and redirected to login page is shown | No Change | Pass
SM_3 |  | Check you can login with NEW password after the password is changed | The User Existed in Database | 1) Enter User Id and "new" Password 2) Submit | user id - user id of above test case password - changed password in above test case | 1) User redirected to manager home page | User redirecting to manager home page | No Change | Pass
SM_4 | Verify Add New Customer & Account Functionality | Check after Adding New Customer, page redirects to details of added customer | The User Existed in Database | 1) Click on Add New Customer 2) Enter Required fields 3) Submit | Customer ID 86241 Customer Name Test Gender male Birthdate 2024-10-10 Address 12 st city City Testcity State teststreet Pin 123456 Mobile No. 12345678 Email test@guru99.com Continue | 1) Details of added Customer must be shown | 1) Details of added Customer must be shown is shown | No Change | Pass
SM_5 |  | Check a new account can be added to new customer | The User Existed in Database | 1) Click on Add New Account 2) Enter all required fields 3) Submit | Created Account details are as follows: Account ID 139192 Customer ID customer id created in above test case Customer Name Test Email test@guru99.com Account Type Savings Date of Opening 2024-10-10 Current Amount 500 Continue | 1) Details of account generated must be shown | 1) Details of account generated must is shown | No Change | Pass
SM_6 | Verify Delete Account & check Mini Statement, Balance Enquiry Functionality | Check confirmation message is shown on deletion of an account | The User Existed in Database | 1) Click on Delete Account 2) Enter required fields 3) Submit | Account No - xyz | 1) A pop - up "Do you really want to delete this account?" | No confirmation message shown | 1) A pop - up "Do you really want to delete this account?" is shown | Pass
SM_7 |  | Check system behaviour after Account is deleted | The User Existed in Database | 1) Click on delete account 2) Enter required fields 3) Submit 4)Click yes in the pop up message shown | Account No - xyz | 1)A message "Account deleted successfully " is shown 2)Page redirected to manager home page | As Expected | No Change | Pass
SM_8 |  | Check that mini statement is not generated for a deleted account | The User Existed in Database | 1) Click on Mini statement 2) Enter deleted account number 3) Submit | Account No - Account No used in above test case | 1) A pop "Account does not exist" 2) Redirects to MiniStatement page | As Expected | No Change | Pass
SM_9 |  | Check balance for deleted account | The User Existed in Database | 1) Click on Balance Enquiry 2) Enter deleted account number 3) Submit | Account No - Account No used in above test case | 1) A pop "Account does not exist" 2) Redirects to Balance Enquiry page | As Expected | No Change | Pass
SM_10 |  | Check that customized statement is not generated for deleted account | The User Existed in Database | 1) Click on Customized statement 2) Enter deleted account no 3) Submit | Account No - Account No used in above test case | 1) A pop up "Account does not exist" 2) Redirects to Customized Statement page | As Expected | No Change | Pass
SM_11 | Verify Delete Customer & Edit customer Functionality | Check confirmation message is shown when customer is deleted | The User Existed in Database | 1) Click on Delete Customer 2) Enter Customer id 3) Submit | customer id - xyz | 1) A pop up "Do you really want to delete this customer?" | No confirmation message shown | 1) A pop up "Do you really want to delete this customer?" is shown | Pass
SM_12 |  | Check that customer should not be deleted if any account exists for that customer | The User Existed in Database | 1) Click on Delete Customer 2) Enter Customer id 3) Submit | customer id - xyz the customer must have at least one account | 1) A pop - up "Customer could not be Deleted.first delete all account of this customer and then delete the customer" 2) Redirect to Customer delete form | As Expected | No Change | Pass
SM_13 |  | Check that a Customer can be Deleted | The User Existed in Database | 1) Click on Delete Customer 2) Enter Customer id 3) Submit | customer id - xyz the customer must have no account | 1) A pop - up "customer deleted successfully" 2) Redirect to Home Page | As Expected | No Change | Pass
SM_14 |  | Check deleted customer cannot be edited | The User Existed in Database | 1) Click on Edit Customer 2) Enter Customer id 3) Submit | Use the customer id of above test case | 1)A pop - up "Customer does not exist" 2) Redirect to Delete customer | A pop up " You are not authorise to delete this account!" redirect to delete customer page | 1)A pop - up "Customer does not exist" 2) Redirect to Edit customer | Pass
SM_15 |  | Check system behaviour when manager deletes a non existing customer ID | The User Existed in Database | 1) Click on Delete Customer 2) Enter Customer id 3) Submit | Use the customer id of above test case | 1)A pop - up "Customer does not exist" 2) Redirects to Delete Customer | alert " You are not authorise to delete this account!" redirect to delete customer page | 1)A pop - up "Customer does not exist" 2) Redirects to Delete Customer is shown | Pass
SM_16 | Verify Fund Transfer & Customized Statement Functionality | Check Fund Transfers | The User Existed in Database | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | payers account no - xyz payee account no - abc amount - 500 Description - cash | 1) Success full message - "Fund Transafer Details for Account No: xyz" 2) Details of fundtransfer | Following message is shown ====================== Amount 600 FROM ACCOUNT NUMBER 143 TO ACCOUNT NUMBER 123 Description cash | No Change | Pass
SM_17 |  | Check Fund Transfer is not done again when page is reloaded | The User Existed in Database | 1) Execute the above test case 2) Refresh Fund Transfer detail page |  | Page should redirect to fund transfer page | Not redirecting to fund transfer page on clicking refresh button | Page is redirecting to fund transfer page | Pass
SM_18 |  | Check transfer details appear on the Customized statement | The User Existed in Database | 1) Click on Mini Statement 2) Enter all required fields 3) Submit | account no - payers account no used in above test case From date - yesterday to date - current date amount lower limit -nil Number of transaction - nil | Statement should show above transactions | As Expected | No Change | Pass
SM_19 |  | Check system behavior when Manager enters wrong Account number during Fund Transfer | The User Existed in Database | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | payers account no - xyz(wrong) payee account no - abc amount - 500 Description - cash | 1) A pop - up " Account # does not exist" | 1) A pop up "No details found for this account!!" | 1) A pop - up " Account # does not exist" is shown | Pass
SM_20 |  | Check System behaviour when manager wants to transfer fund to an account not under his supervision | The User Existed in Database | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | payers account no - xyz payee account no - abc amount - 500 Description - cash | 1) A pop up "You are not authorize to Transfer Funds from this account!!" | 1) A pop up "No details found for this account!!" | 1) A pop up "You are not authorize to Transfer Funds from this account!!" is shown | Pass
SM_21 |  | Check Fund Transfer for same account numbers | The User Existed in Database | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | payers account no - xyz payee account no - xyz amount - 500 Description - cash | 1) A pop up "Payers account No and Payees account No Must Not be Same!!!" | No pop up and fund transfer successful | As expected | Pass
SM_22 |  | Check Fund Transfer when account balance is low | The User Existed in Database | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | payers account no - xyz payee account no - abc amount - 15000 Description - cash | 1) A pop up "Transfer Failed. Account Balance low!!" | 1) A pop up "You cant transfer your account balance is low" | As expected | Pass
SM_23 | Verify Edit Customer Functionality | Check Edit Customer | The User Existed in Database | 1) Click on Edit Customer 2) Enter all required fields 3) Submit |  | 1) Details of edited Customer must be shown | Following details are shown ======================= Customer ID 67902 Customer Name Virendra Gender male Birthdate 2013-11-04 Address Jamnagar City Jamnagar State Gujarat Pin 567321 Mobile No. 8000439024 Email Virendra@gmail.com Continue | No Change | Pass
SM_24 | Verify Deposit Functionality | Check deposit can be made to another account | The User Existed in Database | 1) Click on Deposit 2) Enter all required fields 3) Submit | Account no - xyz | 1) Message - "Transaction details of Deposit for Account xyz" 2) Details of Deposit | Following details are shown ===================== Transaction ID abc Account No xyz Amount Credited 700 Type of Transaction Deposit Description cash Current Balance 5700 Continue | No Change | Pass
SM_25 |  | Check Deposit cannot be made by reload the Deposit detail page | The User Existed in Database | 1) Refresh Deposit detail Page |  | Page should redirect to Deposit Page | Not redirecting to deposit page on clicking refresh button | Page is redirecting to Deposit Page | Pass
SM_26 | Verify Withdrawal and Mini statement & Balance Enquiry Functionality | Check Withdrawal | The User Existed in Database | 1) Determine balance in account Click on Withdrawal 2) Enter all required fields 3) Submit | Account no - xyz | 1) Message - "Transaction details of Withdrawal for Account xyz" 2) Details of withdrawal | Current balance in account is 5700 Following details are shown ===================== Transaction ID 2399 Account No xyz Amount Debited 800 Type of Transaction Withdrawal Description cash Current Balance 4900 | No Change | Pass
SM_27 |  | Check Withdrawal cannot be made if requested amount is more than current amount in the account | The User Existed in Database | 1)Click on Withdrawal 2) Enter all required fields 3) Submit | Account No - xyz Amount - 1600000000 | An Error message "Transaction failed account balance is low !!" | withdrawal done | As expected | Pass
SM_28 |  | Check Mini statement | The User Existed in Database | 1) Click on Ministatement 2) Enter all required fields 3) Submit | Account no - account no of above test case | Details of withdrawal done in above test case | Following details are shown ===================== Transaction ID xyz Account No xyz Amount Debited 800 Type of Transaction Withdrawal Description cash Current Balance 4900 Continue | No Change | Pass
SM_29 |  | Check Balance | The User Existed in Database | 1) Click on Balance enquiry 2) Enter all required fields 3) Submit | Account no - account no of above test case | Details of Balance (check deduction in balance) | Current balance in account is 4900 | No Change | Pass
SM_30 | Verify Customized Statement Functionality | Check Customized statement | The User Existed in Database | 1) Click on customized Statement 2) Enter all required fields 3) Submit | account no - payers account no inserted in above test case From date - yesterday To date - current date Number of transaction - 10 | Details of transactions done in above test case must be shown | Following details are shown ===================== Transaction ID Amount Transaction Type Date of Transaction Description 2398 700 d 2013-11-13 cash 2399 800 w 2013-11-13 cash Continue | No Change | Pass
SM_31 |  | Check Customized statement is not generated when from date is greater than to date | The User Existed in Database | 1) Click on Customized statement 2) Enter all required fields 3) Submit | account no - payers account no inserted in above test case From date - dd/mm/yy to date - lower than from date | 1) pop - up "From date field should be lower than to date field" | 1) pop - up "No transaction details found" | 1) pop - up "From date field should be lower than to date field" is shown | Pass
SM_32 |  | Check Customized statement is generated when from date is less than to date | The User Existed in Database | 1) Click on Customized statement 2) Enter all required fields 3) Submit |  | 1) Message - "Transaction Details for Account No From Date xyz to abc" 2) Details of customized statement | Following details are shown ===================== Transaction ID Amount Transaction Type Date of Transaction Description 2398 700 d 2013-11-13 cash 2399 800 w 2013-11-13 cash Continue | No Change | Pass
SM_33 | Verify Edit account Functionality | Check Edit account | The User Existed in Database | 1) Click on Edit account 2) Enter all required fields 3) Submit | Account no - xyz | 1) Details of updated account must be shown | Following message is shown ============================= Updated Account details are as follows: Account ID xyz Customer ID abc Customer Name Dipen Email Dipen@guru99.com Account Type Current Date of Opening 2013-11-13 Current Amount 4700 Continue | No Change | Pass
SM_34 | Verify Log out Functionality | Check Logout | The User Existed in Database | 1) Click on Log out |  | 1) A pop - "You Have Successfully Logged out" 2) Redirect to Login Page | 1) A pop - "You Have Successfully Logged out" | No Change | Pass
SM_35 | Verify Create Customer id and Password Functionality | Check Customer account created | The User Existed in Database | 1)Click on Add Customer Page 2)Enter Suitable Password 3)Customer should be successfully created 4)Note down Customer id and password 5)Logout from and page should be redirected to login page 6)Enter noted Customer id and password in step 3 |  | Customer should be able to login | As Expected | No Change | Pass
SC_1 | Verify Change Password and Log in Functionality | Check incorrect Old Password | The User Existed in Database | 1) Click on Change Password 2) Enter required fields 3) Submit | Old Password - Incorrect Old Password New password - 123456 Confirm Password - 123456 | 1) A pop-up "Old password is incorrect" is shown 2) User redirected to Change Password | 1) A pop-up "Old password is incorrect" is shown 2) User redirect to Change Password is shown | 1) A pop-up "Old password is incorrect" is shown 2) User redirect to Change Password is shown | Pass
SC_2 |  | Check after password is changed page is redirected to Log in screen | The User Existed in Database | 1) Click on Change Password 2) Enter required fields 3) Submit | Old Password - correct Old Password New password - 123456 Confirm Password - 123456 | 1) A pop-up "Password is changed" is shown 2) User logged out and redirected to log in page | 1) A pop-up "Password is changed" is shown 2) User logged out and redirected to log in page is shown | 1) A pop-up "Password is changed" is shown 2) User logged out and redirected to log in page is shown | Pass
SC_3 |  | Check you can log in with NEW password after the password is changed | The User Existed in Database | 1) Enter User Id and "new" Password 2) Submit | user id - user id of above test case password - changed password in above test case | 1) User redirected to customer home page | As Expected | As Expected | Pass
SC_4 | Verify Balance enquiry Functionality | Check Balance of an account | The User Existed in Database | 1) Click on Balance enquiry 2) Enter all required fields 3) Submit | account no- xyz | Balance of account is shown | As Expected | As Expected | Pass
SC_5 | Verify Mini statement Functionality | Check transfer details appear on the Mini statement | The User Existed in Database | 1) Click on Mini Statement 2) Enter all required fields 3) Submit | Account No - xyz | Last five transactions must be shown | Following detail is shown ======================= Transaction ID Amount Transaction Type Date of Transaction Description 2398 700 d 2013-11-13 cash 2399 800 w 2013-11-13 cash | As Expected | Pass
SC_6 | Verify Fund Transfer & customized statement, Balance enquiry Fucntionality | Check Fund Transfer can be done | The User Existed in Database | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | Payers account no -abc Payees account no -aac Amount -10 Description - fund | Fund transfer should complete successfully | As Expected | As Expected | Pass
SC_7 |  | Check Fund Transfer is not done when page is reloaded | The User Existed in Database | 1) Refresh Fund Transfer detail Page shown in above test case |  | Redirect to Fund Transfer input Page | Not redirecting and fund is transfer again | Funds not transfers again and Page Redirects to Fund Transfer input Page | Pass
SC_8 |  | Check transfer details appear on the Customized statement | The User Existed in Database | 1) Click on Customized Statement 2) Enter all required fields 3) Submit | account no - payers account no used in above test case inserted in above test case From date - dd/mm/yy to date - current date | Customized statement should be shown | Following detail should shown ======================= Transaction ID Amount Transaction Type Date of Transaction Description 2398 700 d 2013-11-13 cash 2399 800 w 2013-11-13 cash | As Expected | Pass
SC_9 |  | Check Fund transfer for Payer Authorization | The User Existed in Database | 1) Click on Fund Transfer 2) Enter wrong Payer account number which is not associated with customer 3) Submit | Payers account no -acc(not associated with customer) Payees account no -xyz Amount -10 Description - fund | Display alert message "You are not authorize to Transfer Funds from this account!! " | Not displaying alert message and transfers the fund successful | 1) A pop is shown "You are not authorize to Transfer Funds from this account!! " 2) Page redirected to Fund Transfer Page | Pass
SC_10 |  | Check Fund transfer Payer or Payee account no does not exist in database | The User Existed in Database | 1) Click on Fund Transfer 2) Enter wrong Payer or Payees account number which is not available in database 3) Submit | Payers account no -abc Payees account no -xyz Amount -10 Description - fund | Display alert message " Account ### does not exist!!! " | Display alert message " No details found for this accounts !!! " | As Expected | Pass
SC_11 |  | Check Fund transfer Payer & Payees account no are same | The User Existed in Database | 1) Click on Fund Transfer 2) Enter same Payer account number and Payees account number which is available in database 3) Submit | Payers account no -xya Payees account no -abc Amount -10 Description - fund | Display alert message " Payers account No and Payees account No Must Not be Same!!! " | Display alert message " No details found for this accounts !!! " | As Expected | Pass
SC_12 | Verify Mini statement Functionality | Check a customer can see mini statement of ONLY his account | The User Existed in Database | 1) Click on Mini Statement 2) Enter all required fields 3) Submit | Account No - xyz(Account does not belong to customer) | Display alert message " You are not authorize to generate statement of this Account!! " | Mini statement is generated for any account that exists in database | As Expected | Pass
SC_13 |  | Check system behavior when wrong account number is entered in the Mini statement | The User Existed in Database | 1) Click on Mini Statement 2) Enter all required fields 3) Submit | Account No - xyz | Display alert message " Account does not exist! " on click ok Redirect to Minisatement input page | As Expected | As Expected | Pass
SC_14 | Verify Customized statement Functionality | Check a customer can see Customized statement of ONLY his account | The User Existed in Database | 1) Click on customize statement 2) Enter all required fields 3) Submit | account no - xyz From date - dd/mm/yy to date - current date Number of transaction - 10 | Display alert message " You are not authorize to generate statement of this Account!! " | Customized statement is generated for any account that exists in database | 1) A pop is shown "You are not authorize to generate statement of this Account!! " 2) Page redirected to Customised Statement Page | Pass
SC_15 |  | Check system behavior when wrong account number is entered in the Customized statement | The User Existed in Database | 1) Click on customize statement 2) Enter all required fields 3) Submit | account no -abc From date - dd/mm/yy to date - current date | Display alert message " Account does not exist! " | As Expected | As Expected | Pass
SC_16 |  | Check system behavior when to-date is lower than from-date in the Customized statement | The User Existed in Database | 1) Click on customize statement 2) Enter all required fields 3) Submit | account no - abc From date - to date - lower than from date amount lower limit - Number of transaction - 10 | Display alert message " FromDate field should be lower than ToDate field!!" | Display alert message " No details found for this accounts !!! " | 1) Display alert message " FromDate field should be lower than ToDate Field.!!! " | Pass
WS_1 | Verify Log in credentials For SinkMiniStatement Functionality | Check Customer id cannot be empty | The User Existed in Database | 1) Do not enter a value in Customer id Field in URL 2) Press Enter | http://demo.guru99.com/V4/sinkministatement.php?CUSTOMER_ID=&PASSWORD=cust123&Account_No=123 | An error message "Log-in Credentials Incorrect" in json format must be shown | As Expected | As Expected | Pass
WS_2 |  | Check Invalid Customer Id | The User Existed in Database | 1) Enter Customer Id which does not exists in database 2) Submit | http://demo.guru99.com/V4/sinkministatement.php?CUSTOMER_ID=12345&PASSWORD=cust123&Account_No=123 | An error message "Log-in Credentials Incorrect" in json format must be shown | As Expected |  | Pass
WS_3 |  | Check Password Cannot be empty | The User Existed in Database | 1) Do not enter a value in Password Field in URL 2) Press Enter | http://demo.guru99.com/V4/sinkministatement.php?CUSTOMER_ID=68195&PASSWORD=&Account_No=1 | An error message "Log in Credentials Incorrect" in json format must be shown | As Expected |  | Pass
WS_4 |  | Check Invalid Password | The User Existed in Database | 1) Enter Password which is not stored in database | http://demo.guru99.com/V4/sinkministatement.php?CUSTOMER_ID=68195&PASSWORD=12345&Account_No=1 | An error message "Log in Credentials Incorrect" in json format must be shown | As Expected |  | Pass
WS_5 | Verify Account number For SinkMiniStatement Functionality | Check Account Number exist in database | The User Existed in Database | 1) Enter a value in Account Number Field in URL which is exist in database 2) Press Enter | http://demo.guru99.com/V4/sinkministatement.php?CUSTOMER_ID=68195&PASSWORD=1234!&Account_No=1 | A Success message with mini statement in the json format should be displayed | As Expected | As Expected | Pass
WS_6 |  | Check Account number cannot be empty | The User Existed in Database | 1) Do not enter a value in account number in URL | http://demo.guru99.com/V4/sinkministatement.php?CUSTOMER_ID=68195&PASSWORD=1234!&Account_No= | An error in message "No Data " should be displayed in json format | As Expected |  | Pass
WS_7 |  | Check json format | The User Existed in Database |  | http://demo.guru99.com/V4/sinkministatement.php?CUSTOMER_ID=68195&PASSWORD=1234!&Account_No=1 |  |  |  | Pass
WS_8 | Verify Log in credentials for SinkBalanceEnquiry Functionality | Check Non Exist Account Number in database | The User Existed in Database | 1) Enter a value in Account Number Field in URL which is not exist in database 2) Press Enter | http://demo.guru99.com/V4/sinkbalanceenquiry.php?CUSTOMER_ID=68195&PASSWORD=1234!&Account_No=185 | An error message "No Data" in format of json should be displayed | As Expected | As Expected | Pass
WS_9 | Verify For SinkBalanceEnquiry Functionality | Check Account Number is Empty | The User Existed in Database | 1) Do not Enter Account Number Field in URL 2) Press Enter | http://demo.guru99.com/V4/sinkbalanceenquiry.php?CUSTOMER_ID=68195&PASSWORD=1234!&Account_No= | A success message with data associated with all account number in json format should be displayed | As Expected | As Expected | Pass
WS_10 | Verify Manager Id For SinkBalanceEnquiry Functionality | Check Valid manager id | The User Existed in Database | 1) Enter manager id which is exist in database 2) Submit | http://demo.guru99.com/V4/sinkbalanceenquiry.php?CUSTOMER_ID=mgr123&PASSWORD=mgr123&Account_No=1 | An Error Message "Log in Credentials Incorrect" should be displayed in json format | As Expected | As Expected | Pass
WS_11 | Verify Customer Id For SinkBalanceEnquiry Functionality | Check Customer id cannot be empty | The User Existed in Database | 1) Do not enter a value in Customer id Field in URL 2) Press Enter | http://demo.guru99.com/V4/sinkbalanceenquiry.php?CUSTOMER_ID=&PASSWORD=1234!&Account_No=1 | An error message "Log in Credentials Incorrect" in json format must be shown | As Expected | As Expected | Pass
WS_12 |  | Invalid Customer Id | The User Existed in Database | 1) Enter Customer Id which is not exist in database 2) Submit | http://demo.guru99.com/V4/sinkbalanceenquiry.php?CUSTOMER_ID=customer123&PASSWORD=1234!&Account_No=1 | An error message "Log in Credentials Incorrect" in json format must be shown | As Expected |  | Pass
WS_13 | Verify Password For SinkBalanceEnquiry Functionality | Check Password Cannot be empty | The User Existed in Database | 1) Do not enter a value in Password Field in URL 2) Press Enter | http://demo.guru99.com/V4/sinkbalanceenquiry.php?CUSTOMER_ID=68195&PASSWORD=&Account_No=1 | An error message "Log in Credentials Incorrect" in json format must be shown | As Expected | As Expected | Pass
WS_14 |  | Check Invalid Password | The User Existed in Database | 1) Enter Password which is not stored in database | http://demo.guru99.com/V4/sinkbalanceenquiry.php?CUSTOMER_ID=68195&PASSWORD=123&Account_No=1 | An error message "Log in Credentials Incorrect" in json format must be shown | As Expected |  | Pass
WS_15 | Verify Account number For SinkBalanceEnquiry Functionality | Check Account Number exist in database | The User Existed in Database | 1) Enter a value in Account Number Field in URL which is exist in database 2) Press Enter | http://demo.guru99.com/V4/sinkbalanceenquiry.php?CUSTOMER_ID=68195&PASSWORD=1234!&Account_No=1 | A Success message with data in the format of json should be displayed | As Expected | As Expected | Pass
WS_16 |  | Check Non Exist Account Number in database | The User Existed in Database | 1) Enter a value in Account Number Field in URL which is not exist in database 2) Press Enter | http://demo.guru99.com/V4/sinkbalanceenquiry.php?CUSTOMER_ID=68195&PASSWORD=1234!&Account_No=15 | An error message "No Data" in format of json should be displayed | As Expected |  | Pass
WS_17 |  | Check Account Number is Empty | The User Existed in Database | 1) Do not Enter Account Number Field in URL 2) Press Enter | http://demo.guru99.com/V4/sinkbalanceenquiry.php?CUSTOMER_ID=68195&PASSWORD=1234!&Account_No= | A success message with data associated with all account number in json format should be displayed | As Expected |  | Pass
WS_18 | Verify Manager Id For SinkBalanceEnquiry Functionality | Check Valid manager id | The User Existed in Database | 1) Enter manager id which is exist in database 2) Submit | http://demo.guru99.com/V4/sinkbalanceenquiry.php?CUSTOMER_ID=mgr123&PASSWORD=mgr123&Account_No=1 | An Error Message "Log in Credentials Incorrect" should be displayed in json format | As Expected | As Expected | Pass

## Status (hidden)
PASS
FAIL
N/A
N/E